## Project Summary
Project Name | Module 3 Progress Test
Project Code | M3-TEST-001
Category | Commercial
Location | Hyderabad
Start Date | 2026-09-03
End Date | 2026-12-31
Budget | 500000
Status | In Progress

## Daily Progress
Date | Work Category | Activity | Completion % | Contractor | Workers Present | Workers Absent | Machinery Used | Materials Used | Weather | Safety Observation | Quality Remarks | Quality Verified | Delay Hours | Delay Reason | Comments
2026-09-04 | Foundation | Foundation excavation continued | 60 | ABC Construction | 22 | 1 | 2 Excavators | 150 Cement Bags | Sunny | No safety issues observed | Excavation quality verified | FALSE | 0 |  | Foundation excavation progressing well
2026-09-05 | Foundation | Foundation excavation and soil preparation completed | 75 | ABC Construction | 24 | 2 | 2 Excavators, 1 Concrete Mixer | 150 Cement Bags, 20 Tons Sand | Partly Cloudy | All workers used helmets, safety shoes and reflective jackets | Foundation excavation depth inspected and approved | FALSE | 1 | Minor excavator maintenance caused a short delay | Foundation work is progressing well and reached 75% completion
2026-09-05 | Electrical | Electrical wiring installation | 25 | ABC Construction | 15 | 2 | 1 Drilling Machine | 50 Electrical Cables | Sunny | Safety equipment used by all workers | Initial wiring inspection completed | FALSE | 0 | No delay | Electrical wiring work started successfully
2026-09-05 | Electrical | Electrical wiring installation | 25 | ABC Construction | 15 | 2 | 1 Drilling Machine | 50 Electrical Cables | Sunny | Safety equipment used by all workers | Initial wiring inspection completed | FALSE | 0 | No delay | Electrical wiring work started successfully
2026-09-05 | Electrical | Electrical wiring installation | 25 | ABC Construction | 15 | 2 | 1 Drilling Machine | 50 Electrical Cables | Sunny | Safety equipment used by all workers | Initial wiring inspection completed | FALSE | 0 | No delay | Electrical wiring work started successfully
2026-09-06 | Foundation | Foundation excavation | 100 | ABC Construction | 25 | 2 | 2 Excavators | 200 Cement Bags | Sunny | All workers using PPE | Work inspected | FALSE | 0 |  | Foundation work progressing
2026-09-06 | Foundation | Foundation excavation | 100 | ABC Construction | 25 | 2 | 2 Excavators | 200 Cement Bags | Sunny | All workers using PPE | Work inspected | TRUE | 0 |  | Foundation work progressing

## Weekly Progress
Week Start | Week End | Work Completed | Completion % | Worker Hours | Major Activities | Delays | Safety Incidents | Overall Status
2026-09-01 | 2026-09-07 | Foundation excavation progressed to 60% and initial structural work started. | 45 | 296 | Foundation excavation, initial structural work | No major delays | No safety incidents | In Progress
2026-09-01 | 2026-09-07 | Foundation excavation and soil preparation progressed significantly during the week | 60 | 1152 | Foundation excavation, soil preparation, site leveling | Minor equipment adjustment caused a 1-hour delay | No safety incidents reported | In Progress

## Delay Records
Delay Date | Reason | Duration Hours | Affected Work | Impact
2026-09-03 | Heavy rainfall | 48 | Foundation Work | Foundation activities delayed by 2 days
2026-09-03 | Material delivery delay | 24 | Concrete Work | Concrete work delayed by 1 day
2026-09-03 | Equipment breakdown | 12 | Excavation Work | Excavation work delayed by 12 hours
2026-09-05 | Heavy rainfall | 3 | Foundation excavation | Foundation excavation delayed by 3 hours

## Milestones
Title | Description | Due Date | Status
M3 Notification Test | Testing milestone completion notification | 2026-09-20 | Completed
M3 Notification Integration Test | Testing milestone completion notification | 2026-09-25 | Completed
Foundation Work | Complete foundation excavation | 2026-09-30 | Completed